Workplan for the preparation of draft decision guidance documents

| Tasks to be carried out | Responsible persons | Deadlines |
| --- | --- | --- |
| Draft an internal proposal based on the information available to the Committee | Chair Drafter | 19 December 2025 |
| Send the draft internal proposal to the drafting group members for comments via email | Secretariat | 19 December 2025 |
| Replies | Drafting group members | 19 January 2026 |
| Update the internal proposal on the basis of comments from drafting group members | Chair Drafter | 19 February 2026 |
| Send the updated internal proposal to the Committee members and observers for comments via email | Secretariat | 19 February 2026 |
| Replies | Committee members and observers | 19 March 2026 |
| Draft a decision guidance document on the basis of the comments of the Committee members and observers | Chair Drafter | 15 April 2026 |
| Send the draft decision guidance document to the drafting group members for comments via email | Secretariat | 15 April 2026 |
| Replies | Drafting group members | 4 May 2026 |
| Finalize the draft decision guidance document on the basis of the comments of the drafting group members | Chair Drafter | 25 May 2026 |
| Send the draft decision guidance document to the Secretariat | Chair Drafter | 25 May 2026 |
| Submit the draft decision guidance document for consideration by the Committee at its twenty-second meeting | Secretariat | 3 August 2026 |